## Slide 1
Akrivia Health / Global Minds Proteomics Update
2026-Feb-10

## Slide 2
Agenda

## Slide 3
Agenda
Action Item Review
Team Updates
  Created Domino workspace
  Installed needed software
  Started review of dataset
Open Q&A, Discussion, and Timelines

## Slide 4
Meeting Minutes & Action Items

## Slide 5: Minutes from 2026-Feb-10
Action Item Review
Corey: Reviewed all action items and all were completed right after the Kickoff Meeting.
Updates and QC Update
Julie: Reviewed the data and identified that 1 specific diagnosis class is missing its label, with 17 samples marked as "Other, please specify". Joe: Confirmed he will go back to Akrivia to ask about these.
Julie: Shared 4 diagnosis categories that have less than 10 samples each: brief psychotic disorder, mania, hypomania, and postnatal depression, which cannot be used for differential abundance analysis.
Julie: Proposed merging the related classes into three main groups: bipolar + mania and hypomania, psychosis + brief psychotic disorder, and depression + postnatal depression. Joe: Agreed with the proposed class merging approach.
Julie: Confirmed she would exclude the 17 unclassified samples from the initial analysis until further clarification is received from Joe.
Julie: Highlighted the 2 data files are available for analysis: one ANML normalized and one raw data file. Joe/Julie: Agreed with the preference to work with the raw data for QC and normalization.
Joe: Offered to provide details about what normalization was done on the other file and any other metadata, which Julie expressed interest in reviewing for use in comparison and correlation during the DAA.
Joe: Highlighted there are 2 other activities that are also on-going, but these are moving slower. These were 1. Genomics sequence data analysis. 2. Clinical questionnaire data being analyzed. Joe: Mentioned he would review the clinical data progress next week as it may contain relevant co-morbidities and self-reported information useful for Julie's differential analysis.
Julie: Outlined her next steps to start on the QC and Normalization work for the next meeting
Corey: Presented a project Gantt/Timeline showing Julie working ~50% on this project with steps from the proposal translated to days, targeting completion around March 16 if there are no analysis changes.

## Slide 6: Action Items
Action Items from 2026-Feb-10 Meeting
Joe: Joe to reach out to Akrivia to get clarification about the 17 samples labeled as 'other' - IN PROGRESS
Joe: Provide Julie with any additional details about the normalization process that was applied to one of the data files - IN PROGRESS
Julie: Start on the QC and normalization process – IN PROGRESS
Joe: Check on the progress of clinical data analysis and share any relevant co-morbidities or self-reported information that might be useful for differential analysis in next week's meeting – IN PROGRESS
Action Items from 2026-Feb-03 Meeting
Joe: Provide access to the MS Teams folder containing the Akrivia clinical XLS files – COMPLETED, 2026-Feb-06
Farzad: Create a new Domino project and upload the proteomics data files for the analysis – COMPLETED, 2026-Feb-03
Corey: Setup weekly calendar cadence for the team to meet – COMPLETE, 2026-Feb-03

## Slide 7
Team Updates & QC of SomaScan dataset

## Slide 8: Dataset review
Diagnosis | Number of samples
Bipolar | 80
Brief psychotic disorder | 1
Dementia | 125
Depression | 149
Mania/Hypomania | 1
Postnatal depression | 3
Psychosis | 35
Schizoaffective disorder | 10
Schizophrenia | 44
"Other please specify" | 17
Diagnosis classes with less than 10 samples cannot be used for DA analysis.
A diagnosis class is missing a label (for 17 samples e.g. sample with barcode_id: 10,
pni_id: "6b1e30b3...")

## Slide 9: Dataset review
Diagnosis | Number of samples
Bipolar + Mania/Hypomania (bipolar disorders) | 80 + 1
Psychosis + Brief psychotic disorder (psychotic disorders) | 35 + 1
Depression + Postnatal depression (depressive disorders) | 149 + 3
Dementia | 125
Schizoaffective disorder | 10
Schizophrenia | 44
Suggested solution for small classes: merging related diagnosis classes to have at least
10 samples per class.

## Slide 10: Next steps
  QC and normalization of Somascan dataset
  Available adat files:
    L0125004546_v5.0_EDTAPlasma.bridge.hybNorm.medNormInt.plateScale.leakDetection.calibrate.anmlQC.qcCheck.adat
    L0125004546_v5.0_EDTAPlasma.bridge.hybNorm.medNormInt.plateScale.leakDetection.calibrate.anmlQC.qcCheck.anmlSMP.adat

## Slide 11
2026
2026
Global Minds / Akrivia Proteomics Analysis
Today
Feb
Mar
Feb 3 - Feb 9
Onboarding, Environment Setup, Data Import into Domino
5 days
Feb 10 - Feb 13
Data Normalization & QC
4 days
Feb 16 - Feb 23
6 days
Diff Abundance Analysis (DAA)
Feb 24 - Mar 3
Pathway Analysis
6 days
Mar 4 - Mar 9
Compare Treatment-Resistant Patients vs Reponders
4 days
Mar 10 - Mar 12
Correlate Proteomics Levels to Clinical Data
3 days
Mar 13 - Mar 16
Reporting & QC
2 days
J&J: Akrivia Health SomaLogic Proteomics Analysis Timeline
Timeline
On-Boarding (4 hours)
Data Retrieval, Normalization, & QC (16 hours)
Differential Abundance Analysis (DAA) (24 hours)
Pathway Analyis (24 hours)
Compare treatment-resistant patients vs responders (16 hours)
Correlate proteomics levels to clinical data (12 hours)
Reporting & QC (8 hours)
Total: 104 hours Bioinformatics; 10 hours Project Management.